## Example
Your Name | Matt Blaul
Project Name | SkyPi |  |  | You must provide accurate artifacts created by you. For example
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 12 | A, B, C, F, I, J, N | Created github repo, met with group to discuss reqs, created powerpoint, created initial API | Requirements, System Architecture, Project Plan Update, Configurations, Presentation | github.com/mblaul/skypi, skypi/core/api, Gdrive
Sprint # 2 | 20 | A, B, C, E, F, H, I, J, L, M, N | Configuring mongodb/cloud server, deploying app to cloud platform, user roles and auth, training users on API, installed additional security protocols | Architecture, Project Plan Update, Configurations, Deployment | github.com/mblaul/skypi/api, Google Team Drive, Postman Documentation | /core/api/*, /core/api/models/User.js, /core/api/models/Weather.js, /core/api/controllers/user.js, /core/api/controllers/weather.js
Sprint # 3 | 18 | A, B, C, D, E, F, H, I, J, M, N | Coded react front end, group communication, Coordinated with group and assigned tasks, two group meetings, researched bootstrap landing pages, Stakeholder meeting with TARDEC | Architecture, Project Plan Update, User Interface Design, User Stories, Tools Tech ETC | github.com/mblaul/skypi/api, github.com/mblaul/skypi/frontend, Google Team Drive, https://drive.google.com/drive/u/1/folders/0ADmYitmSMBPCUk9PVA Team Trello, https://trello.com/skypitasksseniordesign/home | /core/api/*, /frontend/client/src/App, /frontend/client/src/compenents/layout/Navbar, /frontend/client/src/compenents/authentication/Login, /frontend/client/src/compenents/authentication/Register, /frontend/client/src/compenents/content/Landing
Sprint # 4 | 24 | A, B, C, D, E, F, H, I, J, M, N | Coordinated with group and assigned tasks, two group meetings, implemented device favoriting, user verification, admin routes/links, added stations/station page, added Last Updated to Dashboard page | Architecture, Project Plan Update, User Interface Design, User Stories, Tools Tech ETC | github.com/mblaul/skypi/api, github.com/mblaul/skypi/frontend, Google Team Drive, https://drive.google.com/drive/u/1/folders/0ADmYitmSMBPCUk9PVA Team Trello, https://trello.com/skypitasksseniordesign/home | /core/api/*, /frontend/client/src/App, /frontend/client/src/compenents/authentication/Verify, /frontend/client/src/compenents/content/dashboard/Dashboard, /frontend/client/src/compenents/content/stations/Stations, /frontend/client/src/compenents/content/station/Station, /frontend/client/src/actions/* /frontend/client/src/reducers/*
Sprint # 5 | 16 | A, B, C, D, E, F, H, I, J, M, N | Group meetings, assigned tasks, worked on backend getting data by data, search functionality for data by locations | Architecture, Project Plan Update, User Interface Design, User Stories, Tools Tech ETC | github.com/mblaul/skypi/api, github.com/mblaul/skypi/frontend, Google Team Drive, https://drive.google.com/drive/u/1/folders/0ADmYitmSMBPCUk9PVA Team Trello, https://trello.com/skypitasksseniordesign/home | /core/api/controllers/weather.js, /core/api/routes/weather.js, /frontend/client/src/App.js, /frontend/client/src/compenents/content/dashboard/Dashboard.js, /frontend/client/src/compenents/content/station/Station.js, /frontend/client/src/compenents/content/station/Location.js, /frontend/client/src/compenents/content/station/Locations.js, /frontend/client/src/compenents/content/user/Settings.js, /frontend/client/src/actions/weatherActions.js, /frontend/client/src/reducers/weatherRedcuer.js, /frontend/client/src/actions/weatherActions.js,
Sprint # 6

## Count
Your Name |  | Matt Blaul
Project Name |  | SkyPi
Objectives
Sprint# | Team Member | A | B | C | D | E | F | G | H | I | J | K | L | M | N
1 | Matt Blaul | Objectives A: 1; Objectives B: 2; Objectives C: 1; Objectives F: 1; Objectives H: 2; Objectives I: 4; Objectives J: 1; Objectives N: 1
2 | Matt Blaul | 1 | 1 | 3 |  | 1 | 2 |  | 1 | 6 | 2 |  |  | 1 | 1
3 | Matt Blaul | 1 | 3 | 3 | 5 | 1 | 1 |  | 1 | 3 | 1 |  |  | 1 | 5
4 | Matt Blaul | 1 | 2 | 2 | 4 | 1 | 1 |  | 2 | 4 | 1 |  |  | 1 | 6
5 | Matt Blaul | 1 | 1 | 1 | 3 | 2 | 1 |  | 2 | 3 | 1 |  |  | 1 | 4
6