## Example
Your Name | Daniel Ciesielski
Project Name | SkyPi |  |  | You must provide accurate artifacts created by you. For example
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 5 | b,d,g,n | Collaborated with team on high level plans / responsibilities, designed webpage mockup | Requirements, webpageMockup_01.pptx | skypi\frontend
Sprint # 2 | 15 | a,b,c,h,i, | Worked on several tutorials for JS and React / begun implementing frontend webpage | ribbon.js, ribbon.css | skypi\frontend\SkyPIsite | https://reactjs.org/tutorial/tutorial.html#setup-for-the-tutorial https://reactjs.org/docs/create-a-new-react-app.html#create-react-app inspect tool file:///C:/gitRepo/skypi/frontend/SkyPIsite/index.html The "Grasshopper: Learn to Code for Free" app by Area 120 on the PlayStore
Sprint # 3 | 20 |  | Worked on more tutorials, helped build dashboard page, helped build login page, meet with sponser | dashboard.js login.js projectmanager | skypi\fronted\client\src sprint03\projectmanager | https://www.youtube.com/watch?v=A71aqufiNtQ
Sprint # 4 | 30 |  | created stations page, admin button / page foundations, dashboard chart, stations favorite buttons | Navbar.js Stations.js Dashboard.js Timegraph.js AdminPage.js | skypi\frontend\client\src\components\layout skypi\frontend\client\src\components\content\user ..\stations ..\dashboard ..\admin
Sprint # 5 | 42 |  | logout modal, delete profile modal, dashboard charts, stations favorite buttons | LogoutModal.js Navbar.js DeleteModal.js Stations.js Dashboard.js Timegraph.js AdminPage.js | skypi\frontend\client\src\components\layout skypi\frontend\client\src\components\content\user ..\stations ..\dashboard ..\admin | https://www.npmjs.com/package/react-modal https://www.w3schools.com/cssref/pr_class_position.asp
Sprint # 6
Sprint # 7
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | John Doe
Project Name |  | SkyPi
Objectives
Sprint# | Team Member | A | B | C | D | E | F | G | H | I | J | K | L | M | N
0 | [Total] | 4 | 5 | 3 | 5 | 2 | 3 | 5 | 4 | 4 | 2 | 3 | 1 | 2 | 3
1 | Daniel Ciesielski | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2 | Daniel Ciesielski | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1
3 | Daniel Ciesielski | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
4 | Daniel Ciesielski | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
5 | Daniel Ciesielski | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
6 | Daniel Ciesielski
7 | Daniel Ciesielski
8 | Daniel Ciesielski