## Example
Your Name | Matt Blaul
Project Name | SkyPi |  |  | You must provide accurate artifacts created by you. For example
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 12 | A, B, C, F, I, J, N | Created github repo, met with group to discuss reqs, created powerpoint, created initial API | Requirements, System Architecture, Project Plan Update, Configurations, Presentation | github.com/mblaul/skypi, skypi/core/api, Gdrive
Sprint # 2 | 20 | A, B, C, E, F, H, I, J, L, M, N | Configuring mongodb/cloud server, deploying app to cloud platform, user roles and auth, training users on API, installed additional security protocols | Architecture, Project Plan Update, Configurations, Deployment | github.com/mblaul/skypi/api, Google Team Drive, Postman Documentation | /core/api/*, /core/api/models/User.js, /core/api/models/Weather.js, /core/api/controllers/user.js, /core/api/controllers/weather.js
Sprint # 3 | 7 |  | 10/4 - Coded react front end, group communication, tardec visit
Sprint # 4
Sprint # 5
Sprint # 6
Sprint # 7
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | Matt Blaul
Project Name |  | SkyPi
Objectives
Sprint# | Team Member | A | B | C | D | E | F | G | H | I | J | K | L | M | N
1 | Matt Blaul | Objectives A: 1; Objectives B: 2; Objectives C: 1; Objectives F: 1; Objectives H: 2; Objectives I: 4; Objectives J: 1; Objectives N: 1
2 | Matt Blaul | 1 | 1 | 3 |  | 1 | 2 |  | 1 | 6 | 2 |  |  | 1 | 1
3
4
5
6
7
8
9